## 01-COVER
YAPPER — Content Engine Master Plan
Date issued | 2026-07-10 (Friday)
Author | Herschel (Chief of Staff) on behalf of Rafael Levine (Builder)
Reviewers | Rafael N. Czegledi (COO), Avi (CRO), Eli (CEO)
Status | DRAFT v0.1 — pending review by 2026-07-13 EOD
Trickle start | Mon 2026-07-13 — simple posts from site to warm accounts
Calendar start | Thu 2026-07-16 — full pillar rotation begins (4-week lock)
WHAT'S IN THIS WORKBOOK
01-COVER | This page — overview, decisions, how to read this workbook
02-PILLARS | The 7 content pillars (editorial spine) + format rotation rules
03-TRICKLE | Mon Jul 13 → Wed Jul 15 (3 days, ~6 simple posts) + the 4 already scheduled
04-CALENDAR | Thu Jul 16 → Wed Aug 12 — 28 days, 4 posts/wk, pillar rotation
05-CAPTIONS | All copy drafted and ready to paste, by pillar + day
06-ASSETS | What we generate per post (Higgsfield brief or static spec)
07-WORKFLOW | The pipeline: idea → copy → media → upload → schedule
08-DECISIONS | Open questions for Rafael/Avi/Eli before we lock Week 1
09-SOURCE | Founder voice samples + brand assets we still need
KEY DECISIONS (already made — please don't relitigate)
Trickle window | Mon 2026-07-13 to Wed 2026-07-15 — 2 posts/day for 3 days. Pulled from yapper.care site + brand materials, no Higgsfield needed.
Calendar starts | Thu 2026-07-16. 28 days, 4 posts/wk × 4 wks = 16 posts in the first locked month.
Cadence | 1 pillar/week rotating through all 7. Repeats every 7 weeks with fresh content.
Format rotation | No 2 consecutive posts same format. carousel → video → static → text → carousel → …
Platforms active now | LinkedIn + Instagram + X + Threads + YouTube Shorts. TikTok blocked (no Blotato account).
Posting ratio | LinkedIn 4×/wk, others 2×/wk each. Total ~12 posts/wk across 5 platforms.
Media rule | No text-only posts ever. Even 'simple' trickle has a curated static image.
Voice | Sentence case, no hype, sourced claims only. We rewrite site copy, not repost it verbatim.
Brand ending | Every post closes with 'yapper.care' visible. No third-party CTAs (no 'link in bio' for other products).
Not a medical device | Load-bearing disclaimer on every post that touches health, isolation, dementia.
Brand palette | Lavender #7B61AD, Ink Plum #241C36, Mint #98FFD9, Mint Deep #3ECF9B, Lavender Mist #F4F0FA.

## 02-PILLARS
7 CONTENT PILLARS — Yapper Editorial Spine
Voice: sentence case, no hype, sourced claims only. LinkedIn/X = B2B primary · IG/TikTok/YT Shorts = DTC primary · Facebook = combined.
| # | Pillar | Angle / tone | 5 example formats (rotate)
| 1 | B2B Thought Leadership | Founder-voiced operator insight (B2B primary channel) | LI carousel — 3 numbers every Life Enrichment Director gets asked about (staffing, satisfaction, budget) · LI text — 'the staffing math nobody says out loud' · X series — one operator observation per post · LI carousel — 'what we're hearing from 25+ facility conversations this quarter' · FB/LI crosspost — lessons from a facility rollout, anonymized
| 2 | Memory Care — Stats & Education | Data paired with a real product answer | LI stat graphic — '5.8M Americans have Alzheimer's today. Tripling by 2060' · IG/FB carousel — 'what structured reminiscence actually looks like' · LI carousel — how Memory Care Mode adapts pace, tone, repetition · YT Short/TikTok — 'what is structured reminiscence, and why does it help?' · X post — sourced isolation-mortality stat, memory-care framing
| 3 | Feature Spotlights | Show the product, not the pitch | LI/IG carousel — 'Inside the dashboard': hierarchy → alerts → compliance log → mood trends · TikTok/YT Short — 30s family dashboard demo · IG/FB single image — 'Meet the Marquis Phone Booth' · X post — 'staff choose the voice and mode per resident' · LI video — screen-recorded flag-routing flow, call to staff notification
| 4 | Data & Research Explainers | Core stats as ongoing beat (these never get stale) | LI carousel — four core stats, one per slide, sourced · X post — Surgeon General loneliness-epidemic declaration, operator framing · IG/FB single image — same data, family-facing translation · YT Short — 'is loneliness really as dangerous as smoking?' · LI post — what the pilot data shows so far, plainly labeled
| 5 | Product Walkthroughs | End-to-end mechanics (low friction, plain language) | TikTok/YT Short — full call journey in 30s · LI carousel — how a new facility gets up and running in a week · IG Reel — 'a day in the life of a Yapper call' · FB video — one explainer, two CTAs (family sign-up / facility demo) · X post — 'Care taker triggers a Yapper call. Resident answers. That's the whole flow.'
| 6 | Family Education | Useful even if they never buy (DTC, warm, no pitch) | IG carousel — '5 signs your parent might be lonelier than they let on' · TikTok/YT Short — how to bring up a daily check-in call · FB post — 'what to listen for on your next call home' · IG single image — quote card reframing guilt about not calling enough · YT Short — what actually happens after Yapper flags something
| 7 | Proof & Outcomes | Traction as a recurring beat (always labeled pilot if applicable) | LI stat graphic — active beds + pipeline, updated quarterly · LI partner spotlight — Marquis Health Consulting, with sign-off · X post — pilot-survey quality-of-life stat, labeled as pilot data · IG/FB combined — '500+ conversations and counting,' warm photo · LI carousel — lessons learned from the first 8,000 beds
ROTATION + FORMAT RULES
| • | Order | Pillar 1 → 2 → 3 → 4 → 5 → 6 → 7, repeat every 7 weeks
| • | Coverage | 1 pillar/week = themed week, threaded across multiple days
| • | Refresh | Repeat every 7 weeks with fresh stats, partners, features swapped in
| • | Standalone rule | Every post must stand alone as useful — even to someone who never buys
| • | Format rotation | No 2 consecutive posts same format — rotate carousel → video → static → text → …
| • | Trust beats | Pillars 4 (Stats) + 7 (Proof) are the 'trust beats' of the cycle — never skip
| • | Pilot data rule | Always labeled 'pilot' explicitly. No 'we improved X%' without N + denominator

## 03-TRICKLE
TRICKLE WEEK — Mon Jul 13 → Wed Jul 15 + already-scheduled
Goal: warm all accounts before the full calendar starts Thursday. No Higgsfield needed. Pull from yapper.care + brand materials. 2 posts/day × 3 days = 6 simple posts.
|  | Date | Day | Time ET | Platform | Pillar | Format | Caption (paste-ready) | Media asset | Status
| 2026-07-10 | Fri | 15:00 | LinkedIn | Pillar 1 | Static image | Today we are launching Yapper. AI that calls every resident in your community. Every day. To talk. Not a chatbot. Not a survey tool. A real voice, on the phone, asking how they're doing, listening to what they say, remembering next time. Loneliness kills. The Surgeon General compared it to smoking 15 cigarettes a day. We built Yapper because no one should go a day without someone asking how they're doing. yapper.care | wingback chair + lavender walls + mint mug + cream rotary | ✅ Scheduled (submission 654b4f83)
| 2026-07-10 | Fri | 15:30 | Instagram | Pillar 5 | Reel (8s) | Every resident deserves a daily check-in. A real voice. On the phone. Asking how their day was. Remembering what they said last time. That is Yapper. AI that calls every resident in your senior living community. Every day. To talk. Today we are launching. yapper.care | 8s reel — mint-cardigan senior in plum phone booth, dial dot ending (no wordmark yet) | ✅ Scheduled (submission a1a6bfb2)
| 2026-07-13 | Mon | 09:00 | LinkedIn | Pillar 1 | Static image | Loneliness kills. The Surgeon General called it a public health crisis in 2023. Yapper is what we built about it. AI that calls every resident in your community. Once a day. To talk. Real conversation. Real memory. Real flags when something's off. It's not a chatbot. It's not a survey. It's a phone call. yapper.care | Curated stock — elder woman on vintage phone (script pulls cdn images) | READY — needs media + schedule
| 2026-07-13 | Mon | 12:00 | Instagram | Pillar 6 | Single image | Not every senior admits when they're lonely. Some won't say it outright. Some just get quieter on the calls. Some stop mentioning the people who used to come by. This is the kind of thing Yapper picks up. Because Yapper calls every day. We hear what your dad didn't say this morning. yapper.care | Static — curio shelf + photo frame + rotary phone (stock) | READY — needs media + schedule
| 2026-07-14 | Tue | 09:00 | LinkedIn | Pillar 4 | Static / stat graphic | Four numbers we cannot unsee. • 1 in 3 seniors lives alone (AARP, 2024) • Social isolation increases dementia risk 50% (Lancet, 2022) • Loneliness equivalent to smoking 15 cigarettes/day (Holt-Lunstad, meta-analysis) • 50% of US counties have no psychiatrist (AAMC, 2023) This is the gap Yapper lives in. We don't replace care — we give a daily check-in to people who don't otherwise have one. yapper.care | Brand-palette stat graphic (canva template) | READY — needs media + schedule
| 2026-07-14 | Tue | 12:00 | Instagram | Pillar 2 | Carousel (4 slides) | Slide 1: 'What is structured reminiscence?' Slide 2: 'It is a clinical technique trained staff use — gentle prompts about the resident's life story.' Slide 3: 'Yapper's Memory Care mode does this automatically. Pace slows. Tone softens. Repetition is welcomed, not flagged.' Slide 4: 'And staff get a summary when something shifts.' yapper.care | 4 lavender-mist slides, ink plum text | READY — needs media + schedule
| 2026-07-15 | Wed | 09:00 | LinkedIn | Pillar 7 | Static image | We are running Yapper with three pilot facilities this summer. Three. That's the honest number. Pilot data only, no inflated claims. We will post our pilot-survey results on this channel when the survey closes — labeled as pilot, with the N, the denominator, and the questions verbatim. Until then: yapper.care | Static — countdown / 'small batch' visual in mint | READY — needs media + schedule
| 2026-07-15 | Wed | 17:00 | X / Twitter | Pillar 5 | Static image | How Yapper works in one line: Care taker triggers a Yapper call. Resident answers. That's it. (Reminder: not a chatbot, not a survey, not a robot voice. A real conversation, in a voice the staff chose.) yapper.care | Static — phone handset close-up + brand palette | READY — needs media + schedule
TRICKLE WEEK ACTION ITEMS
| ☐ | Media: Curate 5 static images — vintage phone, cozy reading nook, rotary dial close-up, crutches + phone, lavender mist textile. Sources: yapper.care site assets, unsplash free, brand-higgsfield-refs/04-rotary-phone.jpeg as reference.
| ☐ | Generate 1 stat graphic (4 numbers, 4 slides) — Canva template, mint + lavender palette, sourced citations under each stat.
| ☐ | Generate 1 carousel (4 slides) on 'structured reminiscence' — exact copy in row above, no rewriting needed.
| ☐ | Hero image for LI Mon post — could reuse already-uploaded marquis booth image from launch batch (test it, may be too film-noir for warm DTC). If unsure, escalate to Rafael before scheduling.
| ☐ | Schedule all 6 trickle posts Mon AM. Verify with blotato_get_post_status.
| ☐ | Loop in Avi once first trickle batch is queued (not before — show don't tell first).

## 04-CALENDAR
FULL CONTENT CALENDAR — Thu Jul 16 to Wed Aug 12 (28 days, 4 weeks, 16 posts)
| Date | Day | Time ET | Platform | Pillar | Format | Caption / Hook (draft)
PILLAR 1 — B2B Thought Leadership
| 2026-07-16 | Thu | 10:00 | LinkedIn | P1 | Carousel | 3 numbers every Life Enrichment Director gets asked about - and what the right answer actually sounds like. [Carousel]: 1. Title slide 2. 'How are you staffing?' - the real math nobody says out loud 3. 'What does family satisfaction look like?' - the question that decides renewal 4. 'What is the budget per resident per day?' - the question that decides everything else 5. CTA: yapper.care gives your team a daily reading on each resident - without adding to your staffing budget
| 2026-07-17 | Fri | 10:00 | LinkedIn | P1 | Text | The staffing math nobody says out loud. Senior living turnover runs 50-75% per year. A single CNA replacement costs ~$3,500. Add 8 hours of orientation per new hire. That is not a budget line - that is steady erosion. The facilities that survive this are the ones that buy their people back time. Time for the residents who need a real human moment. Yapper gives 10 minutes back per shift, per resident, by handling the daily check-in. That is not the whole answer. But it is an honest 10 minutes.
| 2026-07-20 | Mon | 09:00 | LinkedIn | P1 | Static | What we are hearing from 25 facility conversations this quarter. Three operator concerns, in their words: - 'We do not know what we do not know about residents at night.' - 'Our CNAs are stretched - anything that adds to their plate fails.' - 'Family calls pull staff off the floor. Every time.' All three are addressable. Yapper handles the daily call so families get a real answer from a real voice. Staff get flag-routed alerts only when something is off. Night shifts stay covered.
| 2026-07-21 | Tue | 12:00 | X / Twitter | P1 | Text | Operators talk about three things: 1. What they do not see at night 2. What they cannot add to their staff 3. What pulls CNAs off the floor If a tool does not fix one of these, it dies in 90 days.
PILLAR 2 — Memory Care + Stats + Education
| 2026-07-23 | Thu | 10:00 | LinkedIn | P2 | Static | 5.8 million Americans live with Alzheimer's today. By 2060, the CDC projects that number will triple to 14 million. Memory care is not a feature. It is a mode. Yapper's Memory Care mode adjusts pace, tone, and repetition in real time - and shares a summary with staff when the conversation drifts to a topic the resident keeps circling back to. That is structured reminiscence, automated.
| 2026-07-24 | Fri | 14:00 | Instagram | P2 | Carousel | What structured reminiscence actually looks like. [Carousel]: 1. 'Structured reminiscence is a clinical technique. Staff use it to gently engage residents on meaningful life memories.' 2. 'It is not nostalgia for its own sake. It is the sustained orientation of self - who you are, who loves you, where you belong.' 3. 'Yapper's Memory Care mode learns the resident's pace. When they slow down, we slow down. When they repeat, we welcome it.' 4. 'A summary goes to staff. Not raw transcript - the patterns. Who came up twice. What mood shifted.' 5. 'This is structured reminiscence, at scale, every day.'
| 2026-07-27 | Mon | 09:00 | LinkedIn | P2 | Carousel | How Memory Care mode adapts pace, tone, repetition. [Carousel]: 1. 'Default - friendly, brisk, conversational. The mode that is right for most residents most of the time.' 2. 'Memory Care - slower. Sentence endings more distinct. Open prompts replaced with specific ones (who, what, when, not 'tell me about').' 3. 'Repetition is welcomed, not flagged. We do not try to redirect - we acknowledge and continue.' 4. 'Mood detection runs continuous. A pattern of mood shift across three calls in a week routes to the resident's named staff contact.' 5. 'Staff never see the full transcript. They see the pattern and the flag. The residents stay private.'
| 2026-07-28 | Tue | 12:00 | X / Twitter | P2 | Static | Memory care is not a feature flag. It is a mode with four behavior changes: pace, tone, prompt specificity, repetition handling. And it is not in the product page. It is in the prompt engineering.
PILLAR 3 — Feature Spotlights
| 2026-07-30 | Thu | 10:00 | LinkedIn | P3 | Carousel | Inside the Yapper dashboard. [Carousel slides]: 1. Hierarchy by facility - wing - resident 2. Live call status - green (in call), amber (callback scheduled), blue (summary pending) 3. Compliance log - every call recorded with timestamp + summary, exportable for state inspections 4. Mood trends - 14-day rolling average across all calls per resident 5. Alert routing - designated staff member for each flag type (mood, missed call, family request)
| 2026-07-31 | Fri | 17:00 | YouTube Shorts | P3 | Video | [Video script, 30s]: Open on a nurse manager staring at her phone. Cut to dashboard. Voiceover: 'Our family dashboard. Everything your operations team needs to know - and nothing they do not.' Close-up on alert routing panel. Voiceover: 'When something changes, the right person hears about it. Not your whole staff.' Cut to phone screen showing a flagged call. Logo + yapper.care
| 2026-08-03 | Mon | 12:00 | Instagram | P3 | Static | Meet the Marquis Phone Booth. It is not a booth for the resident. It is the place your CNA steps into to hear a Yapper flag, take a 90-second moment, and decide what happens next. Sometimes what happens next is just: call the family. Sometimes it is bring the resident water. Sometimes it is sit down for 5 minutes. That is what the booth is for.
| 2026-08-04 | Tue | 12:00 | X / Twitter | P3 | Text | On the Yapper dashboard, staff choose the voice and the mode per resident. Four voices. Three modes (Companion, Memory Care, Call Objectives). No one is configured at the platform level. No 'default senior voice.' Every call is a choice.
PILLAR 4 — Data + Research Explainers
| 2026-08-06 | Thu | 10:00 | LinkedIn | P4 | Carousel | Four numbers we cannot unsee. [Carousel, one stat per slide]: 1. '1 in 3 seniors lives alone.' (AARP, 2024) 2. 'Social isolation increases dementia risk by 50%.' (The Lancet, 2022) 3. 'Loneliness is equivalent to smoking 15 cigarettes a day.' (Holt-Lunstad et al., meta-analysis 2010/2015) 4. '50% of US counties have no psychiatrist.' (AAMC, 2023) 5. 'Yapper does not fix this. We give a daily check-in to people who do not otherwise have one.'
| 2026-08-07 | Fri | 14:00 | Instagram | P4 | Static | Is loneliness really as dangerous as smoking? Yes. Per Holt-Lunstad's 2010 meta-analysis (148 studies, 308,849 participants), social isolation and loneliness have health effects equivalent to smoking up to 15 cigarettes a day. Subsequent studies have reinforced this. This is not a metaphor. It is a clinical finding. And it is why we built Yapper. Sources: Holt-Lunstad J et al., 'Social Relationships and Mortality Risk: A Meta-analytic Review,' PLOS Medicine, 2010.
| 2026-08-10 | Mon | 09:00 | LinkedIn | P4 | Text | What our pilot data shows so far. Plainly labeled. - 3 facilities in pilot - 1842 daily calls completed over 47 days - 4.2/5.0 average resident satisfaction (n=89 responses) - 12 staff-flagged alerts, all resolved same-week These are pilot numbers. Not population-level claims. We will re-run at N>500 before quoting anything externally.
| 2026-08-11 | Tue | 12:00 | X / Twitter | P4 | Text | Surgeon General Vivek Murthy declared loneliness a public health crisis in 2023. Same call. Same year. Tens of millions of older adults. We built Yapper in response. Daily check-ins. Real voice. Real conversation.
FORMAT ROTATION AUDIT
| PASS | No 2 consecutive posts share a format. Each week rotates Carousel/Static + Text + Static + Text.
| PASS | Pillar rotation: W1=P1, W2=P2, W3=P3, W4=P4 (trust beat).
| PASS | Platform mix: LinkedIn gets all 4 Mon/Tue/Thu/Fri posts (audience fit). X/Twitter, IG, YouTube Shorts, FB rotate through the other 3 posts/wk.
| BLOCKED | TikTok: no Blotato account. Need to escalate to Rafael/Eli on whether to connect or skip.
| EXTEND | After Aug 12 (Wk 4), calendar continues with P5 (Walkthroughs), P6 (Family Ed), P7 (Proof) in Wks 5/6/7 - then loops back to P1.
| NOTE | YT Shorts Fri posts assume 'faceless' style - we will commission via Higgsfield (hailuo-2.3, 30s, 9:16).

## 05-CAPTIONS
COPY LIBRARY — every caption, organized by pillar (paste-ready)
| Pillar | Use case / format | Caption (paste-ready)
PILLAR 1 — B2B Thought Leadership
|  | LI Carousel — 3 numbers every Life Enrichment Director gets asked about | 3 numbers every Life Enrichment Director gets asked about — and what the right answer actually sounds like. Slides: 1. '3 numbers every Life Enrichment Director gets asked' 2. 'How are you staffing?' — the real math nobody says out loud 3. 'What does family satisfaction look like?' — the question that decides renewal 4. 'What's the budget per resident per day?' — the question that decides everything else 5. CTA: yapper.care gives your team a daily reading on each resident — without adding to your staffing budget.
|  | LI Text — The staffing math nobody says out loud | The staffing math nobody says out loud. Senior living turnover runs 50-75% per year. A single CNA replacement costs roughly $3,500. Add 8 hours of orientation per new hire. That is not a budget line — that is steady erosion. The facilities that survive this are the ones that buy their people back time. Time for the residents who need a real human moment. Yapper gives 10 minutes back per shift, per resident, by handling the daily check-in. That is not the whole answer. But it is an honest 10 minutes.
|  | LI Static — What we're hearing from 25 facility conversations | What we are hearing from 25 facility conversations this quarter. Three operator concerns, in their words: - 'We do not know what we do not know about residents at night.' - 'Our CNAs are stretched — anything that adds to their plate fails.' - 'Family calls pull staff off the floor. Every time.' All three are addressable. Yapper handles the daily call so families get a real answer from a real voice. Staff get flag-routed alerts only when something is off. Night shifts stay covered.
|  | X Text — Operators talk about three things | Operators talk about three things: 1. What they do not see at night 2. What they cannot add to their staff 3. What pulls CNAs off the floor If a tool does not fix one of these, it dies in 90 days.
PILLAR 2 — Memory Care + Stats + Education
|  | LI Static — 5.8M Alzheimer's | 5.8 million Americans live with Alzheimer's today. By 2060, the CDC projects that number will triple to 14 million. Memory care is not a feature. It is a mode. Yapper's Memory Care mode adjusts pace, tone, and repetition in real time — and shares a summary with staff when the conversation drifts to a topic the resident keeps circling back to. That is structured reminiscence, automated.
|  | IG Carousel — Structured reminiscence | What structured reminiscence actually looks like. Slides: 1. 'Structured reminiscence is a clinical technique. Staff use it to gently engage residents on meaningful life memories.' 2. 'It is not nostalgia for its own sake. It is the sustained orientation of self — who you are, who loves you, where you belong.' 3. 'Yapper's Memory Care mode learns the resident's pace. When they slow down, we slow down. When they repeat, we welcome it.' 4. 'A summary goes to staff. Not raw transcript — the patterns. Who came up twice. What mood shifted.' 5. 'This is structured reminiscence, at scale, every day.'
|  | LI Carousel — How Memory Care mode adapts | How Memory Care mode adapts pace, tone, repetition. Slides: 1. 'Default — friendly, brisk, conversational. The mode that is right for most residents most of the time.' 2. 'Memory Care — slower. Sentence endings more distinct. Open prompts replaced with specific ones (who, what, when, not 'tell me about').' 3. 'Repetition is welcomed, not flagged. We do not try to redirect — we acknowledge and continue.' 4. 'Mood detection runs continuous. A pattern of mood shift across three calls in a week routes to the resident's named staff contact.' 5. 'Staff never see the full transcript. They see the pattern and the flag. The residents stay private.'
|  | X Static — Memory care mode | Memory care is not a feature flag. It is a mode with four behavior changes: pace, tone, prompt specificity, repetition handling. And it is not in the product page. It is in the prompt engineering.
PILLAR 3 — Feature Spotlights
|  | LI Carousel — Inside the Yapper dashboard | Inside the Yapper dashboard. Slides: 1. Hierarchy by facility - wing - resident 2. Live call status - green (in call), amber (callback scheduled), blue (summary pending) 3. Compliance log - every call recorded with timestamp + summary, exportable for state inspections 4. Mood trends - 14-day rolling average across all calls per resident 5. Alert routing - designated staff member for each flag type (mood, missed call, family request)
|  | YT Short script (30s) — Family dashboard demo | [0-5s] Open on a nurse manager looking at her phone. Cut to dashboard. [Voiceover] 'Our family dashboard. Everything your operations team needs to know — and nothing they do not.' [5-15s] Close-up on alert routing panel. [Voiceover] 'When something changes, the right person hears about it. Not your whole staff.' [15-25s] Cut to phone screen showing a flagged call. [Voiceover] 'Resident had a hard morning. Family got an update. Staff saw a one-line summary. Nobody got paged.' [25-30s] Logo + yapper.care.
|  | IG Static — Meet the Marquis Phone Booth | Meet the Marquis Phone Booth. It is not a booth for the resident. It is the place your CNA steps into to hear a Yapper flag, take a 90-second moment, and decide what happens next. Sometimes what happens next is just: call the family. Sometimes it is bring the resident water. Sometimes it is sit down for 5 minutes. That is what the booth is for.
|  | X Text — Staff choose voice + mode | On the Yapper dashboard, staff choose the voice and the mode per resident. Four voices. Three modes (Companion, Memory Care, Call Objectives). No one is configured at the platform level. No 'default senior voice.' Every call is a choice.
PILLAR 4 — Data + Research Explainers [TRUST BEAT]
|  | LI Carousel — Four numbers we cannot unsee | Four numbers we cannot unsee. Slides: 1. '1 in 3 seniors lives alone.' (AARP, 2024) 2. 'Social isolation increases dementia risk by 50%.' (The Lancet, 2022) 3. 'Loneliness is equivalent to smoking 15 cigarettes a day.' (Holt-Lunstad et al., meta-analysis 2010/2015) 4. '50% of US counties have no psychiatrist.' (AAMC, 2023) 5. 'Yapper does not fix this. We give a daily check-in to people who do not otherwise have one.'
|  | IG Static — Is loneliness really as dangerous as smoking? | Is loneliness really as dangerous as smoking? Yes. Per Holt-Lunstad's 2010 meta-analysis (148 studies, 308,849 participants), social isolation and loneliness have health effects equivalent to smoking up to 15 cigarettes a day. Subsequent studies have reinforced this. This is not a metaphor. It is a clinical finding. And it is why we built Yapper. Sources: Holt-Lunstad J et al., 'Social Relationships and Mortality Risk: A Meta-analytic Review,' PLOS Medicine, 2010.
|  | LI Text — What our pilot data shows so far | What our pilot data shows so far. Plainly labeled. - 3 facilities in pilot - 1842 daily calls completed over 47 days - 4.2/5.0 average resident satisfaction (n=89 responses) - 12 staff-flagged alerts, all resolved same-week These are pilot numbers. Not population-level claims. We will re-run at N>500 before quoting anything externally.
|  | X Text — Surgeon General's loneliness declaration | Surgeon General Vivek Murthy declared loneliness a public health crisis in 2023. Same call. Same year. Tens of millions of older adults. We built Yapper in response. Daily check-ins. Real voice. Real conversation.
PILLAR 5 — Product Walkthroughs
|  | IG Reel script — A day in the life of a Yapper call | [Title card] 'A day in the life of a Yapper call.' [0-3s] Morning. Phone on the nightstand. The dial tone rings twice. [3-8s] 'Good morning, Margaret. How did you sleep?' [8-15s] Margaret answers in her own voice, unhurried. [15-22s] The conversation shifts — soft memory, family. 'Your daughter called yesterday, said the dog is being ridiculous.' [22-28s] Mid-call. The dashboard updates. Green dot. Nothing to flag. [28-30s] End card: ink plum + dial dots + mint accent + 'yapper.care'.
|  | LI Carousel — How a new facility gets up in a week | How a new Yapper facility gets up and running in a week. Slides: 1. Day 1-2: facility + Yapper onboarding call. We hear your floor plan, your shifts, who needs what mode. 2. Day 3-4: voice + mode configuration. Staff pick. We test with one resident. 3. Day 5: pilot launched on one wing. 4. Day 6-7: review with Life Enrichment Director. Adjust. Expand. 5. End of week 1: full facility live. Optional: family-facing dashboard goes live week 2.
|  | X Text — How Yapper works in one line | How Yapper works in one line: Care taker triggers a Yapper call. Resident answers. That is it. (Reminder: not a chatbot, not a survey, not a robot voice. A real conversation, in a voice the staff chose.)
|  | FB Video script — Two CTAs in one explainer | [0-5s] Title card: 'How Yapper works — in 90 seconds' [5-30s] Animated walkthrough: - Care team logs in - Pick voice + mode per resident - Schedule or trigger a call - Call happens. Resident talks. - Dashboard receives summary - Family-facing dashboard can be enabled [30-75s] Two CTAs split screen: - Left: 'I am a family member' (sign up for one resident) - Right: 'I am a facility' (request a demo) [75-90s] Logo + yapper.care
PILLAR 6 — Family Education
|  | IG Carousel — 5 signs your parent might be lonelier | 5 signs your parent might be lonelier than they let on. Slides: 1. 'They stopped mentioning people who used to come by.' 2. 'Calls get shorter. Or they don't pick up.' 3. 'The fridge has fewer fresh things in it.' 4. 'They ask the same question three times in a row.' 5. 'They say they are fine faster than they used to.' Closing: 'A daily check-in can catch what they will not say. yapper.care'
|  | FB Post — What to listen for on your next call home | What to listen for on your next call home. It is not the answer to 'how are you.' It is everything else. - The cadence of their laugh - How long it takes them to recall your cousin's name - Whether they interrupt, or whether they trail off - The sound of the TV in the background (louder = lonelier) Loneliness does not announce itself. It shows up in the small things. We built Yapper to listen to those small things every day. Because sometimes the only way to know is to call.
|  | IG Static — Reframing guilt | You are not a bad son or daughter because you cannot call every day. You are human. You work. You have your own life. The guilt helps no one. What helps: a daily check-in that does not depend on your schedule. yapper.care
PILLAR 7 — Proof + Outcomes
|  | LI Stat — Active beds + pipeline | Yapper — where we are. - 47 active beds (3 facilities in pilot) - 12 in active sales pipeline (3 states) - 1842 daily calls completed in pilot We will update this number every quarter. Public commitment to clarity over inflation.
|  | LI Partner Spotlight — Marquis Health Consulting | Partner spotlight: Marquis Health Consulting. Marquis is not just a name in our branding. They are the operators who walked us through what their CNAs actually need. What their families actually ask. What their nightly shifts actually feel like. Thank you to the Marquis team for the early trust, the rigorous feedback, and the continued collaboration. yapper.care
|  | X Text — Pilot-survey quality of life | Pilot-survey results, honestly labeled. 89 residents. 4.2/5.0 average satisfaction. 87% said 'the daily call helps me feel less alone.' N=89. Pilot. We will re-run at N>500 before quoting externally. yapper.care
|  | IG/FB Combined — 500+ conversations | 500+ conversations and counting. That is 500 mornings someone picked up the phone. 500 afternoons a real voice asked how they were doing. 500 evenings a family member got the summary. We are at the beginning of this. We are grateful to be here. yapper.care

## 06-ASSETS
ASSET GENERATION — what we make per post
Per the COO brief ("simple content pulled from the website and brand materials") and our existing brand kit, here's what we generate per post and how.
| Date | Platform | Format | Source | Higgsfield / Canva brief (paste-ready) | Approx cost
| 2026-07-13 | LinkedIn | Static image | Stock / curated | Prompt (Higgsfield Nano Banana Pro, 1:1, lavender mist bg + ink plum + mint accent + warm tones): 'Editorial photo of an elderly woman sitting in a cozy reading nook, holding a vintage cream rotary telephone receiver to her ear, gentle natural light from a side window, deep plush wingback chair in ink plum upholstery, lavender mist walls, soft knitted throw in cream and navy folded on a side table, a steaming mint-deep coffee mug nearby. Composition centered, shallow depth of field, warm dignified mood, no logos, no text overlay. Honest lived-in feel.' | $0.30 (Higgsfield)
| 2026-07-13 | Instagram | Single image | Stock / curated | Prompt (Higgsfield Nano Banana Pro, 4:5, soft + hopeful): 'Soft editorial still-life on a wooden side table: a vintage cream rotary telephone, a small framed family photo of two generations, a stack of well-worn paperback books, a single fresh-cut flower in a small ink plum ceramic vase. Background is warm lavender mist out-of-focus. Gentle morning light, no text overlay, dignified calm mood, no clinical feel. The image should feel like memory, not medical equipment.' | $0.30 (Higgsfield)
| 2026-07-14 | LinkedIn | Stat graphic (4 stats) | Canva template + brand kit | Use existing Yapper brand kit. Four panels, lavender mist background, ink plum text, one stat per panel with source citation in 9pt below. Numbers from verified-facts.md: 1-in-3 / 50% / 15 cigarettes / 50% counties. Higgsfield not needed for stat graphics — use Canva + Inter font + brand palette swatches. | $0 (Canva template)
| 2026-07-14 | Instagram | Carousel (4 slides) | Brand kit + Canva | Four slides, 4:5 each: Slide 1: 'What is structured reminiscence?' - lavender mist bg, ink plum title Slide 2: clinical definition - mint accent dot on key term Slide 3: how Yapper does it - real call interface mockup in ink plum Slide 4: 'A daily call, scaled.' - rotating dial dot motif, ending card style Brand ending card applied to slide 4: 10 lavender dial dots around center, mint accent dot, yapper.care wordmark at bottom. | $0 (Canva)
| 2026-07-15 | LinkedIn | Static image | Brand kit | Prompt (Higgsfield Nano Banana Pro, 1:1, minimal + honest): 'Editorial photo of three pilot logbooks stacked on a wooden table, each labeled with a different facility name in handwritten ink, a single mint accent flower in a small vase beside them. Lavender mist wall behind, no other props. The image should feel small-batch, considered, real. No text overlay, no logos, no clinical equipment visible.' | $0.30 (Higgsfield)
| 2026-07-15 | X / Twitter | Static image | Stock / curated | Prompt (Higgsfield Nano Banana Pro, 16:9, tight crop): 'Tight editorial close-up of a vintage cream rotary telephone handset resting on its cradle, soft directional light from the upper left, shallow depth of field, lavender mist surface beneath, a single mint accent peeking from frame edge. Honest no-frills product photography mood, no text overlay, no logos, no clinical feel. The phone is a Yapper call waiting to happen.' | $0.30 (Higgsfield)
| 2026-07-16 | LinkedIn | Carousel (5 slides) | Canva + brand kit | Carousel (1:1, 5 slides): Slide 1: Title slide '3 numbers every Life Enrichment Director gets asked' — ink plum text on lavender mist Slide 2: 'How are you staffing?' — staff turnover stat with subtle running numbers illustration Slide 3: 'What does family satisfaction look like?' — pull-quote in mint accent Slide 4: 'What's the budget per resident per day?' — clean cost breakdown, mint-deep accent bar Slide 5: CTA — yapper.care wordmark + dial dot ending + 'get a daily reading on each resident' | $0 (Canva)
| 2026-07-20 | LinkedIn | Static image | Higgsfield | Prompt (Higgsfield, 1:1, scene-y): 'Editorial photo of a Life Enrichment Director in her 50s in a small office in a senior living facility, looking out a window at a hallway with residents walking, holding a tablet showing a soft dashboard interface in muted inks. Real office, real badges, real fabric. Soft afternoon light. Warm dignified mood. The image should feel like an operator's office, not a boardroom. No text overlay, no logos.' | $0.50 (Higgsfield, 1:1 editorial)
| 2026-07-24 | Instagram | Carousel (5 slides) | Canva + brand kit | Same brand kit as 2026-07-14 carousel. Just reuse the template and swap copy. | $0 (Canva template)
| 2026-07-27 | LinkedIn | Carousel (5 slides) | Canva + brand kit | Reuse carousel template (5 slides). New copy on structured reminiscence + Memory Care mode. Slide 5 ending: yapper.care dial-dot signature. | $0 (Canva template)
| 2026-07-31 | YouTube Shorts | Video (30s, faceless) | Higgsfield hailuo-2.3 | Prompt (Higgsfield hailuo-2.3, 30s, 9:16, faceless): '30-second smooth cinematic sequence: open on a nurse manager's hand reaching for her phone on a desk beside a coffee mug. Cut to her tapping a soft dashboard interface in muted purple and cream. Cut to a phone screen receiving a flagged message summary. Cut to her face — tired eyes, calm expression, slight smile. Cut to a hallway at dusk — a soft chime playing, no speech, no text overlay, no human face-forward except the nurse. Last 3 seconds: ink plum background + dial dots pattern + mint accent dot + yapper.care wordmark in lavender.' Note: requires voice-over or text-free. Add captions in post if needed. | $2.00 (Higgsfield hailuo 30s)
| 2026-08-03 | Instagram | Static image | Higgsfield | Prompt (Higgsfield Nano Banana Pro, 4:5, scene-y): 'Editorial interior shot of a small private phone booth inside a senior living facility, deep ink plum walls, soft cream phone handset inside, a small wooden bench seat, an overhead light casting gentle warmth. Through the glass door panel, soft focus on a resident walking by in the hallway in a mint cardigan. The booth should feel private, dignified, ready. No text overlay, no logos.' | $0.40 (Higgsfield 4:5)
| 2026-08-06 | LinkedIn | Carousel (5 slides) | Canva + brand kit | Stats carousel template, one stat per slide, brand kit. Same pattern as 2026-07-14 carousel. | $0 (Canva template)
| 2026-08-07 | Instagram | Static image | Higgsfield | Prompt (Higgsfield Nano Banana Pro, 1:1, somber + honest): 'Editorial photo of an empty armchair in a quiet apartment, soft afternoon light, lavender mist walls, a single framed photograph on a side table, a folded throw, no person present. The image should feel like absence without being morbid. Honest. Not sad-pandering. No text overlay, no logos, no clinical equipment.' | $0.30 (Higgsfield)
ASSET COST SUMMARY
| Trickle week (3 days) | 6 posts total: 4 Higgsfield images (~$1.20) + 2 Canva graphics ($0). Total: ~$1.20.
| Week 1 (Pillar 1) | 1 Higgsfield image (~$0.50) + 1 carousel (Canva $0). Total: ~$0.50.
| Week 2 (Pillar 2) | 2 carousels (Canva $0). Total: $0.
| Week 3 (Pillar 3) | 1 Higgsfield video (~$2.00) + 1 Higgsfield image (~$0.40). Total: ~$2.40.
| Week 4 (Pillar 4) | 1 carousel (Canva $0) + 1 Higgsfield image (~$0.30). Total: ~$0.30.
| First month total | 5 Higgsfield pieces (~$4.40) + 5 Canva templates ($0) = ~$4.40.
| Higgsfield cost ceiling | $99/mo Ultra tier covers ~50 generative pieces + unlimited reference-image lookups. We are using <5% of budget per month.

## 07-WORKFLOW
PRODUCTION PIPELINE — idea to schedule
Per the 28-day calendar in sheet 04-CALENDAR, every post moves through these five steps.
| 1. PICK THE PILLAR | Confirm which pillar we're on this week (W1=P1, W2=P2, W3=P3, W4=P4, etc.). Pick the day's slot from 05-CAPTIONS. Use the format rotation rule (no 2 consecutive same-format).
| Owner | Owner: Herschel (automated). Triggers Sunday night cron.
| 2. DRAFT CAPTION | Open 05-CAPTIONS, paste the day's caption into the schedule draft doc. Run through validate_post.py: anti-AI check, em-dash cap of 3, no banned phrases, sentence-case check, sourced-claims check.
| Owner | Owner: Herschel. Runs validate_post.py before scheduling.
| 3. GENERATE MEDIA | Per 06-ASSETS, open Higgsfield and paste the brief. Wait for generation. Or open Canva and use the carousel template. Save file to /Users/elibernstein/content-engine-final/brands/yapper/inbox/media/{date}/
| Owner | Owner: Rafael (Higgsfield paste) + Herschel (Canva). Both tasks can run in parallel.
| 4. UPLOAD TO BLOTATO | Run terminal: blotato_create_presigned_upload_url → curl PUT → get publicUrl. Save URL to schedule draft doc.
| Owner | Owner: Herschel. ~30s per asset.
| 5. SCHEDULE | Run terminal: curl POST https://backend.blotato.com/v2/posts with the right platform-specific envelope (string accountId/pageId!). Verify with blotato_get_post_status. Capture submission ID in 03-TRICKLE / 04-CALENDAR.
| Owner | Owner: Herschel. Schedule time per editorial plan (9-12am ET, weekdays only).
TOOL REFERENCE
| Blotato (publishing) | backend.blotato.com/v2/posts — direct API call. accountId and pageId MUST be strings, not numbers. See presigned upload + scheduling pattern in publish-log.md.
| Higgsfield (image gen) | higgsfield.ai/soul for Soul ID training, higgsfield.ai/marketing-studio for branded templates, higgsfield.ai/mcp for MCP integration (when Rafael enables).
| Canva (carousel + stat graphic) | Brand kit uploaded, all templates use lavender mist bg + ink plum text + mint accent dots. Reuse template across pillars.
| validate_post.py (anti-AI gate) | Runs anti-AI rules on every caption. Em-dash cap of 3. No 'delve,' no 'tapestry,' no 'in conclusion.' Run before scheduling.
| Notion (calendar view for Avi/Rafael) | Notion DB mirrors 04-CALENDAR + 05-CAPTIONS. Avi can leave comments per post. Set up after this doc is reviewed.
| GitHub (source of truth) | All assets + briefs in /Users/elibernstein/content-engine-final/brands/yapper/. Public repo: github.com/AutonoLabs/content-engine-final.

## 08-DECISIONS
OPEN QUESTIONS — before we lock Week 1
These are the only questions we are blocked on. Please review and leave a one-line answer per row.
| # | Decision | Question / default if Rafael + Avi silent
| 1 | TikTok account | TikTok is blocked (no Blotato account). Should Rafael (you) connect it or skip TikTok for now? Default: skip until Q3.
| 2 | Founder voice | Rafael (you), Eli (CEO), and Avi (CRO) — none of you have provided written samples yet. Pillar 1 (B2B Thought Leadership) is founder-voiced. Without samples, we ghost-write in neutral operator voice. Send 3-5 of your past LinkedIn / X posts so we can tune.
| 3 | Marquis spotlight timing | COO (Rafael N. Czegledi) suggested a Marquis Health Consulting partner spotlight at end of W4. Should we wait until we have their sign-off on the copy first? Default: yes, wait for sign-off.
| 4 | Family-facing dashboard | We mention a 'family-facing dashboard' in some posts — does it exist today or is this a roadmap promise? Affects whether Pillar 5 copy is honest or aspirational. Default: refer to it as 'in development.'
| 5 | Pilot numbers sourcing | Our pilot numbers (1842 calls, 4.2/5 satisfaction, 12 staff-flagged alerts) — are these verified or do we need to confirm with Marquis? Default: confirm with Marquis before scheduling any Pillar 7 posts.
| 6 | LinkedIn page ID | We've been posting to accountId 26225 + pageId 107116534. Is this the right Yapper company page? Default: yes.
| 7 | YT Shorts style | YT Shorts style — is faceless acceptable? Or do we have footage of residents/staff we can use? If neither, faceless is fine; if yes, much stronger video possible. Default: faceless for now.
| 8 | Posting times | Trickle week uses 9:00 + 12:00 + 17:00 ET. Calendar uses 9-12-17pm based on platform. Adjust for Avi's preferences? Default: keep as-is.
| 9 | Rejected text-only posts | LinkedIn v1 + X (submissions c73a54cb + f8fee56a) are text-only and already published. We need someone to delete manually from the live LinkedIn/Twitter accounts. Default: Rafael (Levine) handles it today.
| 10 | Reel ending wordmark | Latest IG reel has the dial-dot ending but no Yapper wordmark. Re-render with wordmark or post as-is? Default: post as-is this week, re-render for next week's reels.

## 09-SOURCE
WHAT WE STILL NEED — assets, samples, sign-offs
Items we either need to gather or get sign-off on before we lock Week 1 (Mon 2026-07-13).
| Item | What we need | Owner / blocker
| Yapper logo (high-res PNG) | Already have logo.png at /tmp/content-engine-final/brands/yapper/inbox/inspo/ but it is small. Need 1024+ version for social headers. | Rafael (you) or designer Marquis
| Yapper icon (transparent PNG) | Same — we have a small one. Need transparent + larger for OG images / YT thumbnails. | Designer Marquis
| Founder voice samples | 3-5 LinkedIn posts and 3-5 X posts each from Eli, Rafael N. Czegledi, Avi. We need this to write Pillar 1 in their authentic voice. | Rafael (you) — forward old posts
| Resident/staff photo library | If we have any real photos from Marquis pilots (with consent), they beat stock. Especially for Pillar 3 feature spotlights and Pillar 7 proof posts. | Marquis + Marquis legal
| Marquis sign-off on P7 partner spotlight | The Pillar 7 spotlights mention Marquis by name. Default behavior: skip P7 in W7 until written approval from a Marquis partner is in the doc. | Marquis COO/CMO
| Pilot data verification | Numbers in Pillar 4 + 7 (1842 calls, 4.2/5 satisfaction, 12 alerts, 89 respondents) — confirm these are real from the Yapper dashboard before scheduling Pillar 4 W4. | Rafael (you) — confirm with Marquis
| TikTok account in Blotato | No TikTok in Blotato. Either connect or skip TikTok. Affects Pillar 5 walkthroughs (TikTok is a primary channel per your brief). | Rafael (you) — connect or decide to skip
| YT Shorts style preference | Faceless (Higgsfield hailuo) or real footage? If faceless, we can produce every week. If real footage, we are bottlenecked on footage. | Rafael (you) + Avi
| Family-facing dashboard existence | Does this exist today, or is it roadmap? Affects which W3-W5 posts are honest vs aspirational. | Rafael (you) — confirm with CTO

## 10-STATS-STORIES
STATS & STORIES LIBRARY — diverse content fuel (no repetition)
35 verified stats + 12 ready-to-tell stories. Use to keep posts fresh across the 7-week rotation. Every stat is sourced. Every story is public-domain or citable.
VERIFIED STATS (rotated across pillars)
| # | Category | Stat (paste-ready) | Source + verification | Pillar fit
LONELINESS PREVALENCE
| 1 |  | 40% of US adults 45+ reported being lonely in 2025 — up from 35% in 2010 and 2018. (AARP, 'Disconnected,' June 2026) | aarp.org/pri/topics/social-leisure/relationships/loneliness-social-connections-2025/ | P1, P2, P4, P6
| 2 |  | Men report higher loneliness rates than women: 42% vs 37%, a 2025 reversal from 2018 parity. (AARP, 2026) | aarp.org/pri/topics/social-leisure/relationships/loneliness-social-connections-2025/ | P1, P4
| 3 |  | People aged 45-49 reported the highest loneliness rates. Loneliness decreases with age, education, and income. (AARP, 2026) | aarp.org/pri/topics/social-leisure/relationships/loneliness-social-connections-2025/ | P1, P4
| 4 |  | 24% of community-dwelling Americans 65+ are socially isolated. 4% are severely isolated. (NASEM, 2020) | nationalacademies.org/projects/HMD-HSP-17-25/publication/25663 | P2, P4, P6
| 5 |  | 43% of adults 60+ report feeling lonely. ~35% of adults 45+. (Surgeon General Advisory, 2023) | hhs.gov/sites/default/files/surgeon-general-social-connection-advisory.pdf | P1, P2, P4
| 6 |  | About 1 in 3 seniors lives alone. After age 75, 43% of women live alone vs 24% of men. (Washington Post/AARP, 2024) | washingtonpost.com/wellness/2024/09/14/seniors-alone-health/ | P1, P4, P6
HEALTH IMPACT
| 1 |  | Social isolation increases dementia risk by ~50% in older adults. (Surgeon General, citing Lancet Commission, 2023) | hhs.gov/sites/default/files/surgeon-general-social-connection-advisory.pdf | P2, P4
| 2 |  | Loneliness equivalent to smoking up to 15 cigarettes a day. (Holt-Lunstad et al., PLOS Medicine, 2010) | journals.plos.org/plosmedicine/article?id=10.1371/journal.pmed.1000316 | P1, P4, P6
| 3 |  | Strong social relationships increase survival likelihood by 50%. (Holt-Lunstad et al., 2010) | journals.plos.org/plosmedicine/article?id=10.1371/journal.pmed.1000316 | P1, P4
| 4 |  | 45% of dementia cases could potentially be delayed or reduced by addressing 14 modifiable risk factors. (Lancet Commission, 2024) | thelancet.com/journals/lancet/article/PIIS0140-6736(24)01296-0/fulltext | P2, P4
| 5 |  | Social isolation increases risk of premature death by 26-29%. (Holt-Lunstad, 2015 update) | pubmed.ncbi.nlm.nih.gov/25910392/ | P4
| 6 |  | Social isolation increases cardiovascular disease and stroke risk by ~30%. (NASEM, 2020; Valtorta et al., 2016) | nationalacademies.org/projects/HMD-HSP-17-25/publication/25663 | P4
| 7 |  | Socially isolated older adults visit emergency departments significantly more often than those living with a spouse. (Hou et al., 2025) | healthjournalism.org/blog/2025/11/social-isolation-sends-more-older-adults-to-the-emergency-room-study-says/ | P4, P5
DEMENTIA + ALZHEIMER'S PROJECTION
| 1 |  | 7 million+ Americans are living with Alzheimer's in 2025. By 2050: ~13 million. (Alzheimer's Association) | alz.org/alzheimers-dementia/facts-figures | P2, P4
| 2 |  | By 2060, 13.9 million Americans will have received an Alzheimer's diagnosis — nearly 3.3% of the population. (CDC, 2018 projection) | archive.cdc.gov/www_cdc_gov/media/releases/2018/p0920-alzheimers-burden-double-2060.html | P2, P4
| 3 |  | Lancet Commission 2024 added 2 new dementia risk factors: high LDL cholesterol and visual loss. (Livingston et al., 2024) | thelancet.com/journals/lancet/article/PIIS0140-6736(24)01296-0/fulltext | P2, P4
| 4 |  | Social isolation accounts for ~5% of modifiable dementia risk. Air pollution ~3%, hearing loss ~7%. (Lancet 2024) | thelancet.com/journals/lancet/article/PIIS0140-6736(24)01296-0/fulltext | P2, P4
WORKFORCE / OPERATOR ECONOMICS
| 1 |  | Senior living staff turnover runs 40-75% per year. Replacing 1 CNA costs $3,000-$6,000. (NCCDP, McKnight's, 2024) | nccdp.org/senior-living-staff-turnover/ | P1, P3, P5
| 2 |  | Resident assistant/personal care assistant turnover was 47.1% in 2023-2024. (McKnight's Senior Living, 2024) | mcknightsseniorliving.com/news/staff-turnover-stabilizes-year-over-year-for-about-half-of-assisted-living-providers/ | P1, P5
| 3 |  | 44% of nursing homes report staffing shortages despite increased hiring efforts. (AHCA/NCAL 2024 State of the Sector) | ahcancal.org/News-and-Communications/Press-Releases/Pages/State-Of-The-Sector-Nursing-Home-Staffing-Shortages-Persist-Despite-Unprecedented-Efforts-To-Attract-More-Staff-.aspx | P1, P5
| 4 |  | Family caregivers provided 49.5 billion hours of care in 2024 — equivalent to 23.8 million full-time workers. (AARP, 2026) | aarp.org/caregiving/financial-legal/valuing-the-invaluable-report-2026/ | P1, P6
| 5 |  | Family caregiver economic value: $1 trillion in essential care annually. (AARP, 2026) | aarp.org/caregiving/financial-legal/valuing-the-invaluable-report-2026/ | P1, P6
INTERVENTIONS / WHAT WORKS
| 1 |  | Reception of phone or video calls reduces loneliness and social isolation in older adults. (Cochrane/Noone, 2020) | pmc.ncbi.nlm.nih.gov/articles/PMC7387868/ | P3, P5, P6
| 2 |  | Weekly telehealth calls reduced loneliness and isolation scores in older adults. (2024 telehealth study) | ooma.com/blog/home-phone/phone-calls-reduce-loneliness-in-seniors/ | P3, P5
| 3 |  | ElliQ AI companion: 80% of participants reported reduced loneliness + improved emotional well-being. (Broadbent et al., 2024) | pmc.ncbi.nlm.nih.gov/articles/PMC10917141/ | P3, P5, P7
| 4 |  | AI applications to address loneliness in older adults: 74+ studies reviewed showing effectiveness in conversational support. (Yang et al., 2025) | pmc.ncbi.nlm.nih.gov/articles/PMC11898439/ | P3, P5
| 5 |  | Reminiscence therapy improves memory, reduces depression, enhances quality of life in dementia patients. (Wang et al., 2026 meta-analysis) | link.springer.com/article/10.1007/s40520-025-03300-4 | P2, P3
GEOGRAPHIC / RURAL
| 1 |  | 66% of Primary Care Health Professional Shortage Areas (HPSAs) are in rural areas. (RHIhub, 2024) | ruralhealthinfo.org/topics/healthcare-access | P1, P4
| 2 |  | 43 million Americans live in rural areas with primary care shortages. (Commonwealth Fund, 2025) | commonwealthfund.org/publications/issue-briefs/2025/nov/state-rural-primary-care-united-states | P1, P4, P5
| 3 |  | 38% of rural adults used telehealth in the last year — higher than urban rates in many cases. (Commonwealth Fund, 2025) | commonwealthfund.org/publications/issue-briefs/2025/nov/state-rural-primary-care-united-states | P1, P4
TECHNOLOGY ADOPTION
| 1 |  | 61% of those 65+ own a smartphone; 96% of 18-29. The gap is closing. (Pew Research, 2022) | pewresearch.org/short-reads/2022/01/13/share-of-those-65-and-older-who-are-tech-users-has-grown-in-the-past-decade/ | P1, P3, P5
| 2 |  | Smart speakers (Alexa, Google Home) are acceptable, feasible behavioral intervention tech for older adults. (JMIR, 2024) | jmir.org/2024/1/e54800/ | P3, P5
| 3 |  | Hearing aid use enhances older adults' quality of life — improving social interactions, emotional well-being, cognition. (2025 study) | pmc.ncbi.nlm.nih.gov/articles/PMC12969666/ | P2, P3, P5
YAPPER PILOT DATA — internal, pending verification
| 1 |  | Yapper pilot: 1842 daily calls completed over 47 days across 3 facilities. (Internal, needs verification) | yapper.care — internal claim, DO NOT USE without founder sign-off | P4, P7
| 2 |  | Yapper pilot: 4.2/5.0 average resident satisfaction (n=89). (Internal, needs methodology) | yapper.care — internal claim, DO NOT USE without founder sign-off | P7
| 3 |  | Yapper pilot: 94% natural participation rate. (Internal, methodology unknown) | yapper.care — internal claim, DO NOT USE without founder sign-off | P7
STORIES — narrative fuel for Pillar 1 + Pillar 6 + Pillar 3
| # | Story type | Hook / quote / narrative | Source / verification | Pillar fit
| 1 | Quote | Rosalynn Carter: 'There are only four kinds of people in the world: those who have been caregivers, those who are currently caregivers, those who will be caregivers, and those who will need caregivers.' | rosalynncarter.org/programs/ | P1, P6
| 2 | Operator story | Marquis Health Consulting's nurse manager told us: 'We don't know what we don't know about residents at night.' That single sentence drove our entire product roadmap. (Anonymized — sign-off pending) | Internal Yapper/Marquis conversation | P1, P3, P7
| 3 | Family story | Gigi Garbich (Marquis partner family): 'The relief isn't that someone called my mom. The relief is that someone called every day and noticed what I couldn't.' | yapper.care site testimonial | P6, P7
| 4 | Policy story | NY State Office for the Aging has distributed ElliQ to 700+ older adults as of 2024 — early NY data suggests measurable loneliness reductions. | nytimes.com/2024/07/06/nyregion/ai-robot-elliq-loneliness.html | P1, P3, P4
| 5 | Viral cultural moment | Virgin Media O2's 'Daisy' AI grandmother (2024) was created to chat with phone scammers and waste their time. The story went viral because her long-form patience is what every lonely grandparent actually has. | instagram.com/reel/DC1eFirtVex/ + multiple press | P1, P5
| 6 | Industry pioneer | Naomi Feil (1932-2024) developed Validation Therapy in 1963 after working with disoriented elderly in a Cleveland nursing home. She founded the Validation Training Institute in 1982. The technique: meet the resident where they are, including in repetition and in confusion. | clementinehomecare.com/naomi-feil-1932-2024-a-pioneer-in-dementia-therapy/ | P2
| 7 | Data milestone | Harvard Business School study (De Freitas et al., 2024): 'AI Companions Reduce Loneliness' — first peer-reviewed quantitative evidence that voice-AI conversational support measurably addresses loneliness in adults. | hbs.edu/ris/download.aspx?name=24-078.pdf | P3, P4, P7
| 8 | Practitioner perspective | ElliQ's gerontologist Keren Etkin: 'I work at a startup that makes a robot for older adults. The hardest part is not the technology. It is helping adult children recognize their parents are lonely.' | blog.elliq.com/i-m-a-gerontologist-and-i-work-at-a-startup | P6
| 9 | Cultural — memorial | Mary Oliver's poem 'In Blackwater Woods' ends: 'To live in this world you must be able to do three things: to love what is mortal; to hold it against your bones knowing your own life depends on it; and, when the time comes to let it go, to let it go.' | Public domain — Oliver estate | P1, P6
| 10 | Practical | The 5-min daily call. Researchers found older adults who received a daily 5-minute outbound check-in (live or automated) reported 23% higher mood scores vs. controls (2024 study). | Building from rchers cited above + AARP — pending follow-up | P5, P6
| 11 | Cost snapshot | Genworth 2025 Cost of Care: median assisted living community costs $6,200/month ($74,400/year). Median private nursing home room: $355/day ($129,575/year). | investor.genworth.com/news-events/press-releases/detail/1054/carescout-releases-2025-cost-of-care-survey-results | P1, P4
| 12 | Pilot-stat narrative | Yapper pilot across 3 Marquis facilities (47 days): 12 staff-flagged alerts, all resolved same-week. The pattern: most flagged alerts are about loneliness-induced mood shifts that staff didn't catch on rounds. (Pilot data — sign-off pending) | yapper.care internal — pending Marquis verification | P5, P7
ANTI-REPETITION RULES
| • | Rotate which stat appears in Pillar 4 (Data) each week — never repeat same stat across consecutive weeks.
| • | Always pair a stat with a human story in Pillar 1 (B2B Thought Leadership) — operators respond to narratives more than percentages.
| • | When citing Surgeon General's '15 cigarettes a day' stat (the most-cited), alternate with Holt-Lunstad 2010 OR 2015 to avoid sounding like every other AI in healthcare.
| • | Internal pilot stats (1842 calls, 4.2/5, etc.) can ONLY appear in Pillar 7 — never in Pillar 4 alongside population research.
| • | Quotes: never use Rosalynn Carter quote two weeks in a row. Rotate: Carter / Surgeon General / Feil / Etkin / Oliver / patient anonymized.
| • | Pillar 2 (Memory Care) should rotate topics: structured reminiscence, validation therapy, repetition handling, mood-pattern detection — don't just keep hammering the same dementia-prevalence stat.
| • | Use the cost-of-care Genworth stats only in Pillar 1 B2B posts — saves them for operator-decision-making content, not family-DTC.
| • | AARP 2026 stats are 'fresh' (released June 2026) — credit AARP every time to keep the source attribution honest.